# Progress Update

IKS-Grounded Multimodal Agricultural Advisory System M.Tech Thesis · IIITDM Jabalpur · Ankit Pawar · Supervisor: Dr. Akshay Pandey Date: 1 September 2026

A short update covering the work completed since the last meeting. The focus of this period was expanding and repairing the classical-text corpus — the limitation identified in the evaluation — and adding the Kashyapiya text.

## 1. Headline

The corpus was expanded and repaired: it now holds 259 passages across five books, up from 206 across four — an increase of +53 passages (+26%). This includes the newly added Kashyapiya Krishisukti and the recovery of text that earlier optical-character-recognition (OCR) had missed.

|  | Before | After |
| --- | --- | --- |
| Books | 4 | 5 |
| Passages (chunks) | 206 | 259 |

## 2. What was done

### 2.1 Added the Kashyapiya Krishisukti (new fifth book)

The 64-page Sanskrit-only scanned text was processed end to end:

- OCR + translation of all 64 pages using Google Gemini (Flash 3.6) — the pages are Devanagari Sanskrit with no existing English translation, so each verse was both transcribed and translated. 857 verses were captured, and the whole book was verified complete (from the opening to the closing colophon).

- The English translation was chunked into 39 passages and added to the corpus in the same format as the other books.

Honest assessment of this book. Verified both against the scholarly edition (Asian Agri-History Foundation, Sadhale & Nene) and by direct testing of the new passages: the Kashyapiya is a cultivation treatise — strong on soil selection, water management, seeds, and sowing, but light on plant-disease treatment. It therefore strengthens the corpus for cultivation and soil/water queries, but is not expected on its own to close the disease-advice gap. For that gap, Vishvavallabha (Chakrapani Mishra, which explicitly covers plant disease and pest management) is the more valuable text to obtain next.

### 2.2 Repaired the existing books (re-OCR)

While preparing the Kashyapiya, a defect was found in the original OCR of the existing books: some pages had been cut short or saved as an error message, because the earlier OCR had an output-length limit. All existing books were re-processed with the newer model and no length limit, one book at a time, with each result verified before it was accepted:

- Vrikshayurveda: 15 pages recovered — 9 that had been dropped entirely (including the Introduction) and 6 that had been cut short. Its passage count rose from 42 to 52.

- Brihat Samhita: one page that had saved an error message, plus 18 truncated pages, were restored. Count went from 136 to 140.

- Krishi Parashara and Upavanavinoda: reviewed and left unchanged (already complete).

Every change was compared against the previous version before acceptance, with no loss of existing content.

### 2.3 Rebuilt the search index

The full corpus was re-embedded and rebuilt into the vector database, and verified to hold exactly 259 passages across the five books.

## 3. Corpus now

| Book | Passages | Focus |
| --- | --- | --- |
| Brihat Samhita | 140 | rainfall, water divining, crops, tree treatment |
| Vrikshayurveda | 52 | plant care, horticulture, pest control |
| Kashyapiya Krishisukti (new) | 39 | soil, water, seed, sowing (cultivation) |
| Upavanavinoda | 15 | arboriculture, plant protection |
| Krishi Parashara | 13 | sowing, seed preservation, calendar |
| Total | 259 |  |

## 4. In progress

- Re-running the evaluation on the expanded corpus, to measure whether the larger corpus reduces the earlier ~55% over-refusal rate (the system correctly declining answerable questions because the texts did not cover them). The evaluation is being re-run now; the comparison of before-vs-after numbers will follow.

## 5. Points to discuss

- Vishvavallabha as the next text. The evidence points to it as the highest-value addition for the disease-treatment gap (it is the same translator family as texts alrea